## schedule
VTrans FRP BMP Implementation | [9 empty] | Plan |  |  | Actual
|  | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4 |  | Phase 5 |  | Phase 6 |  | Phase 7
PERCENT
ACTIVITY | COMPLETE | Implementation Year
|  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
Allen Brook | 0% | bar: Implementation Year 2017 to Implementation Year 2019
Rugg Brook | 0% | bar: Implementation Year 2020 to Implementation Year 2022
Stevens Brook | 0% | bar: Implementation Year 2020 to Implementation Year 2022
Potash Brook | 0% | bar: Implementation Year 2023 to Implementation Year 2025
Centennial Brook | 0% | bar: Implementation Year 2023 to Implementation Year 2025
Indian Brook | 0% | bar: Implementation Year 2023 to Implementation Year 2025
Municipal/VTrans - 1 | 0% | bar: Implementation Year 2026 to Implementation Year 2027
Municipal/VTrans - 2 | 0% | bar: Implementation Year 2028 to Implementation Year 2029
Municipal/VTrans - 3 | 0% | bar: Implementation Year 2030 to Implementation Year 2031
Municipal/VTrans - 4 | 0% | bar: Implementation Year 2032

## Phase 1
Watershed | Site Name | MS4 Impervious Owner | Ownership of Land where BMP is Located | BMP Type | Permit # | Drainage Area (acres) | Impervious Cover Managed (acres) | Impervious Cover Managed (% of Drainage Area) | VTrans Impervious Cover Managed (acres) | VTrans Impervious Cover Managed (% of Total Impervious Cover) | Runoff Channel Protection Volume (CPv) Storage | Runoff Channel Protection Volume (CPv) Storage (ac-ft) | VTrans High-Flow Target Managed (%) | Estimated Cost | Estimated Cost (Rounded to Nearest $1,000) | VTRANS Impervious Acres Managed Score | Runoff Channel Protection Volume Storage Score | Percent Of Vtrans High Flow Target Managed Score | Estimated Cost Score | Ranking Score
Allen | Rest Area Pond Retrofit | VTrans / VT BGS | VTrans | Detention Basin | NP | 26.8016 | 4.4191 | 16.49% | 4.4191 | 100% | 29172 | 0.6697 | 23.77% | 157529.0376 | 158000 | 1 | 2 | 1 | 3 | 7
Allen | Town Office | VTrans | VTrans | Median Filter | NP | 2.2241 | 0.36865 | 16.57% | 0.36865 | 100% | 2660 | 0.061065 | 1.983% | 31920.0484 | 32000 | 1 | 2 | 1 | 4 | 8
Allen | WCA_1 | VTrans | VTrans | Median Filter | NP | 4.2458 | 0.6831 | 16.09% | 0.6831 | 100% | 7643 | 0.17546 | 3.674% | 91716.1376 | 92000 | 1 | 2 | 1 | 4 | 8
Allen | WCA_2 | VTrans | VTrans | Median Filter | NP | 2.511 | 0.43557 | 17.35% | 0.43557 | 100% | 1852 | 0.042516 | 2.343% | 25000 | 25000 | 1 | 2 | 1 | 4 | 8
Allen | WCA_3 | VTrans | VTrans | Median Filter | NP | 2.3157 | 0.55385 | 23.92% | 0.55385 | 100% | 1318 | 0.030257 | 2.979% | 25000 | 25000 | 1 | 2 | 1 | 4 | 8
Allen | WCA_4 | VTrans | VTrans | Median Filter | NP | 3.2504 | 0.70859 | 21.8% | 0.70859 | 100% | 4404 | 0.1011 | 3.811% | 52848.1355 | 53000 | 1 | 2 | 1 | 4 | 8
Allen | VTrans Median A | VTrans | VTrans | Median Filter | NP | 1.2823 | 0.30257 | 23.6% | 0.30257 | 100% | 5040 | 0.1157 | 1.627% | 60480.1551 | 60000 | 1 | 2 | 1 | 4 | 8
Allen | VTrans Median B | VTrans | VTrans | Median Filter | NP | 0.72569 | 0.20857 | 28.74% | 0.20857 | 100% | 3390 | 0.077824 | 1.122% | 40680.1043 | 41000 | 1 | 2 | 1 | 4 | 8
Allen | VTrans Median E | VTrans | VTrans | Median Filter | NP | 1.175 | 0.30085 | 25.61% | 0.30085 | 100% | 3642 | 0.083609 | 1.618% | 43704.1121 | 44000 | 1 | 2 | 1 | 2 | 6
Allen | VTrans Median F | VTrans | VTrans | Median Filter | NP | 1.0651 | 0.20114 | 18.88% | 0.20114 | 100% | 3705 | 0.085055 | 1.082% | 44460.114 | 44000 | 1 | 1 | 1 | 4 | 7
Allen | VTrans Median G | VTrans | VTrans | Median Filter | NP | 1.541 | 0.31754 | 20.61% | 0.31754 | 100% | 5090 | 0.11685 | 1.708% | 61080.1566 | 61000 | 1 | 1 | 1 | 4 | 7
Allen | VTrans Median H | VTrans | VTrans | Median Filter | NP | 1.3011 | 0.24652 | 18.95% | 0.24652 | 100% | 4902 | 0.11253 | 1.326% | 58824.1508 | 59000 | 1 | 2 | 1 | 2 | 6
Allen | VTrans Median I | VTrans | VTrans | Median Filter | NP | 1.6545 | 0.36801 | 22.24% | 0.36801 | 100% | 5846 | 0.13421 | 1.98% | 70152.1799 | 70000 | 4 | 5 | 2 | 2 | 13
Bartlett | Bartlett Bay Treatment System (BBTS) Expansion | VTrans/ South Burlington | South Burlington | Underground Detention Chamber in ROW | 5625-9010, 2-0180, 2-0153 | 16.0589 | 9.1826 | 57.18% | 1.8751 | 20.42% | 23958 | 0.55 | 100% | 378260 | 378000 | 2 | 4 | 4 | 2 | 12
[14 empty] | Total Cost | 1142000

## Phase 2
Watershed | Site Name | MS4 Impervious Owner | Ownership of Land where BMP is Located | BMP Type | Permit # | Drainage Area (acres) | Impervious Cover Managed (acres) | Impervious Cover Managed (% of Drainage Area) | VTrans Impervious Cover Managed (acres) | VTrans Impervious Cover Managed (% of Total Impervious Cover) | Runoff Channel Protection Volume (CPv) Storage | Runoff Channel Protection Volume (CPv) Storage (ac-ft) | VTrans High-Flow Target Managed (%) | Estimated Cost | Estimated Cost (Rounded to Nearest $1,000) | VTRANS Impervious Acres Managed Score | Runoff Channel Protection Volume Storage Score | Percent Of Vtrans High Flow Target Managed Score | Estimated Cost Score | Ranking Score
Rugg | SDC27 | VTrans | VTrans | Median Filter | NP | 1.6133 | 0.42593 | 26.4% | 0.42593 | 100% | 2762 | 0.063407 | 3.099% | 17953 | 18000 | 1 | 2 | 1 | 4 | 8
Rugg | SDC280 | VTrans | VTrans | Median Filter | NP | 2.1271 | 0.37076 | 17.43% | 0.37076 | 100% | 2741 | 0.062925 | 2.698% | 17816.5 | 18000 | 1 | 2 | 1 | 4 | 8
Rugg | SDC29 | VTrans | VTrans | Median Filter | NP | 2.249 | 0.40858 | 18.17% | 0.40858 | 100% | 2358 | 0.054132 | 2.973% | 15327 | 15000 | 1 | 2 | 1 | 4 | 8
Rugg | SDC342 | VTrans | VTrans | Median Filter | NP | 1.596 | 0.31004 | 19.43% | 0.31004 | 100% | 2358 | 0.054132 | 2.256% | 15327 | 15000 | 1 | 2 | 1 | 4 | 8
Rugg | SDC347 | VTrans | VTrans | Median Filter | NP | 1.4011 | 0.30405 | 21.7% | 0.30405 | 100% | 2608 | 0.059871 | 2.213% | 16952 | 17000 | 1 | 2 | 1 | 4 | 8
Rugg | SDC83a | VTrans | VTrans | Median Filter | NP | 1.7062 | 0.26915 | 15.77% | 0.26915 | 100% | 2534 | 0.058173 | 1.959% | 16471 | 16000 | 1 | 2 | 1 | 4 | 8
Rugg | SDC83b | VTrans | VTrans | Median Filter | NP | 1.8029 | 0.36291 | 20.13% | 0.36291 | 100% | 3339 | 0.076653 | 2.641% | 21703.5 | 22000 | 1 | 2 | 1 | 4 | 8
Rugg | SDC87 | VTrans | VTrans | Median Filter | NP | 4.92 | 0.92305 | 18.76% | 0.92305 | 100% | 5579 | 0.12808 | 6.717% | 36263.5 | 36000 | 1 | 2 | 1 | 4 | 8
Stevens | Fairfield Rd / I-89 | VTrans | VTrans | Detention Basin | NP | 28.9226 | 2.0712 | 7.161% | 0.84604 | 40.85% | 29795.04 | 0.684 | 16.6% | 108531.8 | 109000 | 1 | 5 | 1 | 2 | 9
Stevens | Median A1 | VTrans | VTrans | Median Filter | NP | 0.89558 | 0.41595 | 46.45% | 0.41595 | 100% | 2468 | 0.056657 | 8.16% | 27335.568 | 27000 | 1 | 2 | 1 | 4 | 8
Stevens | Median A2 | VTrans | VTrans | Median Filter | NP | 0.651 | 0.29595 | 45.46% | 0.29595 | 100% | 1881 | 0.043182 | 5.806% | 20833.956 | 21000 | 1 | 1 | 1 | 4 | 7
Stevens | SDC105b | VTrans | VTrans | Median Filter | NP | 0.99 | 0.52775 | 53.31% | 0.52775 | 100% | 2333 | 0.053558 | 10.35% | 25840.308 | 26000 | 1 | 1 | 1 | 4 | 7
Stevens | SDC105c | VTrans | VTrans | Median Filter | NP | 0.84 | 0.43724 | 52.05% | 0.43724 | 100% | 1799 | 0.041299 | 8.577% | 19925.724 | 20000 | 1 | 1 | 1 | 4 | 7
Stevens | SDC118 | VTrans | VTrans | Median Filter | NP | 1.0768 | 0.5479 | 50.88% | 0.5479 | 100% | 2544 | 0.058402 | 10.75% | 28177.344 | 28000 | 1 | 2 | 1 | 4 | 8
Stevens | SDC140b | VTrans | VTrans | Median Filter | NP | 1 | 0.50434 | 50.43% | 0.50434 | 100% | 2359 | 0.054155 | 9.894% | 26128.284 | 26000 | 1 | 2 | 1 | 4 | 8
Stevens | SDC408 | VTrans | VTrans | Median Filter | NP | 0.94 | 0.46958 | 49.96% | 0.46958 | 100% | 2047 | 0.046993 | 9.212% | 22672.572 | 23000 | 1 | 1 | 1 | 4 | 7
Stevens | SDC98b | VTrans | VTrans | Median Filter | NP | 0.85 | 0.41674 | 49.03% | 0.41674 | 100% | 1968 | 0.045179 | 8.175% | 21797.568 | 22000 | 1 | 1 | 1 | 4 | 7
Rugg | Exit 19 South | VTrans | VTrans | Detention | NP | 57.9374 | 3.7774 | 6.52% | 3.6721 | 97.21% | 90169.2 | 2.07 | 26.72% | 270000 | 270000 | 3 | 5 | 2 | 2 | 12
[14 empty] | Total cost: | 729000

## Phase 3
Watershed | Site Name | MS4 Impervious Owner | Ownership of Land where BMP is Located | BMP Type | Permit # | Drainage Area (acres) | Impervious Cover Managed (acres) | Impervious Cover Managed (% of Drainage Area) | VTrans Impervious Cover Managed (acres) | VTrans Impervious Cover Managed (% of Total Impervious Cover) | Runoff Channel Protection Volume (CPv) Storage | Runoff Channel Protection Volume (CPv) Storage (ac-ft) | VTrans High-Flow Target Managed (%) | Estimated Cost | Estimated Cost (Rounded to Nearest $1,000) | VTRANS Impervious Acres Managed Score | Runoff Channel Protection Volume Storage Score | Percent Of Vtrans High Flow Target Managed Score | Estimated Cost Score | Ranking Score
Centennial | I-89 Cloverleaf (NE) | VTrans | VTrans | Underground Detention Chamber | NP | 39.1734 | 13.798 | 35.22% | 4.9847 | 36.13% | 102583.8 | 2.355 | 36.74% | 432000 | 432000 | 4 | 5 | 2 | 2 | 13
Potash | Exit 13 | VTrans | VTrans | Gravel Wetland | NP | 16.7225 | 4.7749 | 28.55% | 4.7749 | 100% | 24698.52 | 0.567 | 9.686% | 218795.01 | 219000 | 4 | 4 | 1 | 2 | 11
Potash | Exit 14 | VTrans | VTrans | Gravel Wetland | NP | 4.905 | 1.812 | 36.94% | 1.812 | 100% | 12806.64 | 0.294 | 3.676% | 131084.82 | 131000 | 2 | 3 | 1 | 2 | 8
Potash | I-89 Swale | VTrans | VTrans | Median Filter | NP | 6.2805 | 1.7973 | 28.62% | 1.7973 | 100% | 23130.36 | 0.531 | 3.646% | 129349.296 | 129000 | 2 | 4 | 1 | 2 | 9
Potash | 189 Cloverleaf | VTrans / Town | VTrans | Detention Basin | NP | 21.2549 | 11.5319 | 54.26% | 3.4553 | 29.96% | 49179.24 | 1.129 | 7.009% | 59015.088 | 59000 | 3 | 5 | 1 | 3 | 12
Indian | I-289/Route 15 North | VTrans | VTrans ROW | Median Filter | NP | 2.7812 | 0.85215 | 30.64% | 0.85215 | 100% | 5270.76 | 0.121 | 20.7% | 34259.94 | 34000 | 1 | 2 | 1 | 4 | 8
Indian | I-289/Route 15 South | VTrans | VTrans ROW | Median Filter | NP | 2.1535 | 0.76038 | 35.31% | 0.76038 | 100% | 4443.12 | 0.102 | 18.47% | 28880.28 | 29000 | 1 | 2 | 1 | 4 | 8
[14 empty] | Total Cost | 1033000

## Phase 4
Watershed | Site Name | MS4 Impervious Owner | Ownership of Land where BMP is Located | BMP Type | Permit # | Drainage Area (acres) | Impervious Cover Managed (acres) | Impervious Cover Managed (% of Drainage Area) | VTrans Impervious Cover Managed (acres) | VTrans Impervious Cover Managed (% of Total Impervious Cover) | Runoff Channel Protection Volume (CPv) Storage | Runoff Channel Protection Volume (CPv) Storage (ac-ft) | VTrans High-Flow Target Managed (%) | Estimated Cost | Estimated Cost (Rounded to Nearest $1,000) | VTRANS Impervious Acres Managed Score | Runoff Channel Protection Volume Storage Score | Percent Of Vtrans High Flow Target Managed Score | Estimated Cost Score | Ranking Score
Rugg | I-89 / Holyoke Farm | Town / VTrans | Private | Infiltration | NP | 61.828 | 0.49703 | 0.8039% | 0.24779 | 49.85% | 62116.56 | 1.426 | 1.803% | 185079.5 | 185000 | 1 | 5 | 1 | 2 | 9
Rugg | SASH / Federal St Connector | City/ VTrans | VTrans/ Private | Detention | NP | 21.1188 | 4.8862 | 23.14% | 1.1993 | 24.55% | 15681.6 | 0.36 | 8.728% | 34758 | 35000 | 2 | 3 | 1 | 4 | 10
Rugg | Access Rd. East | VTrans | VTrans/ Private | Detention | NP | 85.1307 | 2.7547 | 3.236% | 2.4187 | 87.8% | 79279.2 | 1.82 | 17.6% | 410000 | 410000 | 3 | 5 | 1 | 2 | 11
Rugg | Access Rd. West | VTrans | VTrans/ Private | Detention | Drains Portion of 1-1428 | 13.7042 | 0.55273 | 4.033% | 0.55273 | 100% | 28401.12 | 0.652 | 4.022% | 125000 | 125000 | 1 | 5 | 1 | 4 | 11
Stevens | Upper Fairfield Hill Rd | VTrans | VTrans/ Private | Detention Basin | NP | 34.2627 | 3.3583 | 9.802% | 1.1547 | 34.38% | 55756.8 | 1.28 | 22.65% | 163761 | 164000 | 2 | 5 | 1 | 2 | 10
Potash | Dorset St / 189 Ramps | VTrans / Town | VTrans | Detention Basin | NP | 9.3633 | 5.5723 | 59.51% | 1.0931 | 19.62% | 15158.88 | 0.348 | 2.217% | 100993.464 | 101000 | 2 | 3 | 1 | 2 | 8
[14 empty] | Total Cost: | 1020000

## Phase 5
Watershed | Site Name | MS4 Impervious Owner | Ownership of Land where BMP is Located | BMP Type | Permit # | Drainage Area (acres) | Impervious Cover Managed (acres) | Impervious Cover Managed (% of Drainage Area) | VTrans Impervious Cover Managed (acres) | VTrans Impervious Cover Managed (% of Total Impervious Cover) | Runoff Channel Protection Volume (CPv) Storage | Runoff Channel Protection Volume (CPv) Storage (ac-ft) | VTrans High-Flow Target Managed (%) | Estimated Cost | Estimated Cost (Rounded to Nearest $1,000) | VTRANS Impervious Acres Managed Score | Runoff Channel Protection Volume Storage Score | Percent Of Vtrans High Flow Target Managed Score | Estimated Cost Score | Ranking Score
Indian | Fairview Dr | Village/ VTrans/ Town | Village | Gravel Wetland | 1-1074 SN002 | 29.399 | 4.1269 | 14.04% | 0.71716 | 17.38% | 28967.2 | 0.67 | 17.42% | 290000 | 290000 | 1 | 5 | 1 | 2 | 9
Potash | Queen City Pk Rd | VTrans / Town | VTrans | Detention Basin | NP | 6.5109 | 2.9228 | 44.89% | 0.43033 | 14.72% | 19689.12 | 0.452 | 0.8729% | 99226.944 | 99000 | 1 | 4 | 1 | 3 | 9
Bartlett | 1690 Shelburne Rd | VTrans/ South Burlington | VTrans/ Developer- Pizzagalli | Underground Detention Chamber in ROW | 5625-9010 | 0.81016 | 0.41585 | 51.33% | 0.41585 | 100% | 1873.08 | 0.043 | 22.18% | 199361.28 | 199000 | 1 | 1 | 1 | 2 | 5
[14 empty] | Total Cost | 588000

## Phase 6
Watershed | Site Name | MS4 Impervious Owner | Ownership of Land where BMP is Located | BMP Type | Permit # | Drainage Area (acres) | Impervious Cover Managed (acres) | Impervious Cover Managed (% of Drainage Area) | VTrans Impervious Cover Managed (acres) | VTrans Impervious Cover Managed (% of Total Impervious Cover) | Runoff Channel Protection Volume (CPv) Storage | Runoff Channel Protection Volume (CPv) Storage (ac-ft) | VTrans High-Flow Target Managed (%) | Estimated Cost | Estimated Cost (Rounded to Nearest $1,000) | VTRANS Impervious Acres Managed Score | Runoff Channel Protection Volume Storage Score | Percent Of Vtrans High Flow Target Managed Score | Estimated Cost Score | Ranking Score
Munroe | M08 Executive Dr Pond | Town/ VTrans | Non-VTrans | Detention Pond | 1-1291 | 91.0957 | 21.3389 | 23.42% | 2.7076 | 12.69% | 23348.16 | 0.536 | 49.8% | 25000 | 25000 | 3 | 2 | 2 | 4 | 11
Munroe | Across from Tractor Supply | Town/ VTrans | VTrans | Gravel Wetland | NP | 6.7808 | 3.7664 | 55.55% | 2.8475 | 75.6% | 23696.64 | 0.544 | 52.37% | 479856.96 | 480000 | 3 | 4 | 3 | 2 | 12
Munroe | By Danform Shoes | Town/ VTrans | VTrans | Underground Detention | NP | 4.8913 | 2.8361 | 57.98% | 2.1238 | 74.89% | 6316.2 | 0.145 | 39.06% | 102322.44 | 102000 | 3 | 2 | 2 | 2 | 9
[14 empty] | Total Cost | 607000

## Phase 7
Watershed | Site Name | MS4 Impervious Owner | Ownership of Land where BMP is Located | BMP Type | Permit # | Drainage Area (acres) | Impervious Cover Managed (acres) | Impervious Cover Managed (% of Drainage Area) | VTrans Impervious Cover Managed (acres) | VTrans Impervious Cover Managed (% of Total Impervious Cover) | Runoff Channel Protection Volume (CPv) Storage | Runoff Channel Protection Volume (CPv) Storage (ac-ft) | VTrans High-Flow Target Managed (%) | Estimated Cost | Estimated Cost (Rounded to Nearest $1,000) | VTRANS Impervious Acres Managed Score | Runoff Channel Protection Volume Storage Score | Percent Of Vtrans High Flow Target Managed Score | Estimated Cost Score | Ranking Score
Centennial | I-89 Outfall | VTrans | VTrans | Detention Basin | NP | 13.0728 | 2.8231 | 21.6% | 2.7718 | 98.18% | 125017.2 | 2.87 | 20.43% | 1419000 | 1419000 | 3 | 5 | 1 | 1 | 10
Moon | Randbury Rd | VTrans/ Town of Rutland | VTrans/ Town of Rutland/ Private | Gravel Wetland | New Road Project (Construction Permit) | 23.0997 | 10.9532 | 47.42% | 2.2918 | 20.92% | 35937 | 0.825 | 196.9% | 279262.1146 | 279000 | 3 | 5 | 4 | 2 | 14
Sunderland | Tracy Rd. | VTrans/ Colchester | VTrans/ Colchester | Infiltration Trench | 6363-INDS | 4.9701 | 3.8932 | 78.33% | 2.3108 | 59.35% | 18513 | 0.425 | 287.9% | 54000 | 54000 | 3 | 5 | 4 | 3 | 15
[14 empty] | Total Cost: | 1752000